## Sheet1
ISSUSE LOCATION | DETAIL | URL | STATUS | COMMENTS
Unable to Flag a comment | On clicking the confirm email link, The page is showing an error | http://wpvm24.cloudapp.net:84/?qa=46/qqqqqqqqqqqqqqqqqqqqqqqqqqqq | Unresolved
Filter by Category - Sidebar | The category links are static | http://wpvm24.cloudapp.net:84/ | Unresolved
Filter by Category - Sidebar | View All Categories link is dead | http://wpvm24.cloudapp.net:84/ | Unresolved
Filter by Category - Sidebar | Search Bar is non-functional | http://wpvm24.cloudapp.net:84/ | Unresolved
Nav Buttons | The CSS is not as per VD | http://wpvm24.cloudapp.net:84/ | Unresolved
Asking Related Question | Spelling mistake to be fixed - This is a samople answer |  | Unresolved
Dead Link | Top right corner RSS feed icon is dead | http://wpvm24.cloudapp.net:84/?qa= | Unresolved
Footer | Footer doesnot stick to the bottom |  | Unresolved
Footer | The feedback and Contact us links are dead |  | Unresolved
Main Nav | Help button is Dead |  | Unresolved
Ask Page - Sidebar | The data is dummy | http://wpvm24.cloudapp.net:84/?qa=ask | Unresolved